## Risk Register
Risk ID | Risk Category | Risk Description | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Rating | Controls in Place | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Status | Owner | Mitigation Plan | Review Date
R1 | Cybersecurity / Human Risk | Phishing attack compromises employee account | 4 | 4 | 16 | High | MFA, email filtering, security awareness baseline training | 3 | 3 | 9 | Medium | In Progress | Security Lead | Monthly phishing simulations; quarterly awareness refreshers; implement conditional access policies | 2025-03-01
R2 | Cloud Security | Misconfigured S3 bucket exposes customer data | 3 | 5 | 15 | High | Default S3 encryption, IAM least privilege, versioning enabled | 2 | 3 | 6 | Medium | In Progress | DevOps | Implement automated S3 configuration scanning (AWS Config); enforce SCPs blocking public buckets | 2025-03-02
R3 | Identity & Access Mgmt | Credential reuse across SaaS tools | 4 | 3 | 12 | Medium | SSO partially enabled, password policy enforced | 2 | 2 | 4 | Low | Mitigated | IT | Enforce full SSO rollout; deploy company-wide password manager; disable local accounts | 2025-03-03
R4 | Endpoint / Device Risk | No endpoint protection on developer laptops | 3 | 4 | 12 | Medium | OS auto-updates, basic antivirus | 2 | 2 | 4 | Low | Mitigated | IT | Deploy EDR across all devices; enforce device compliance policies; block unmanaged laptops | 2025-03-04
R5 | Insider Threat | Insider data misuse by contractor | 2 | 5 | 10 | Medium | RBAC, access logging, contractor NDAs | 2 | 3 | 6 | Medium | In Progress | CTO | Tighten least privilege; enforce privileged access monitoring; quarterly access reviews | 2025-03-05
R6 | Cybersecurity / Ransomware | Ransomware attack halts operations | 2 | 5 | 10 | Medium | Daily backups, email filtering, AV | 2 | 4 | 8 | Medium | In Progress | Security Lead | Implement immutable backups; annual disaster recovery test; EDR behavior monitoring | 2025-03-06
R7 | Vendor Security | Lack of vendor due diligence for SaaS tools | 3 | 3 | 9 | Medium | Basic vendor list maintained; ad hoc reviews | 2 | 2 | 4 | Low | Mitigated | GRC Analyst | Formalize vendor risk questionnaire; enforce pre-procurement reviews; track vendor SLAs + SOC2 reports | 2025-03-07
R8 | Code / DevOps Risk | API key leakage in GitHub repo | 3 | 4 | 12 | Medium | .gitignore, occasional manual checks | 1 | 2 | 2 | Low | Mitigated | DevOps | Add pre-commit secret scanning; automate key rotation; migrate to GitHub environment secrets | 2025-03-08
R9 | Cloud Infrastructure | DDoS disrupts cloud hosting | 2 | 4 | 8 | Medium | Load balancer in place; basic traffic filtering | 1 | 3 | 3 | Low | Mitigated | DevOps | Enable AWS Shield, CloudFront protection; autoscaling tuning; WAF rules for bad IP ranges | 2025-03-09
R10 | Identity Lifecycle | Lack of offboarding process causes lingering access | 3 | 3 | 9 | Medium | Basic HR offboarding checklist | 1 | 2 | 2 | Low | Mitigated | IT | Implement automated deprovisioning via HRIS → SSO; quarterly access recertification; disable stale accounts | 2025-03-10
R11 | Cloud Security | Unpatched EC2 instances vulnerable to known exploits | 3 | 4 | 12 | Medium | Missing patch automation | 2 | 3 | 6 | Medium | In Progress | DevOps | Implement Patch Manager automation; enforce monthly patch cadence | 2025-03-11
R12 | Identity & Access Mgmt | Inactive user accounts remain enabled beyond 90 days | 2 | 4 | 8 | Medium | Ad hoc account cleanup | 1 | 3 | 3 | Low | Mitigated | IT | Implement automated deactivation policy; quarterly access review | 2025-03-12
R13 | Endpoint / Device Risk | Unauthorized USB storage devices used by staff | 3 | 3 | 9 | Medium | Basic USB logging | 2 | 2 | 4 | Low | Mitigated | IT | Deploy device control; enforce USB restriction policy | 2025-03-13
R14 | Insider Threat | Employee downloading large datasets without approval | 3 | 4 | 12 | Medium | CloudTrail logs enabled | 2 | 3 | 6 | Medium | In Progress | Security Lead | Enable anomaly detection; implement DLP policies | 2025-03-14
R15 | Network Security | Weak Wi-Fi encryption in guest networks | 2 | 5 | 10 | Medium | WPA2 still in use | 2 | 3 | 6 | Medium | In Progress | Network Engineer | Upgrade to WPA3; segregate guest VLAN | 2025-03-15
R16 | Application Security | SQL injection risk due to unvalidated inputs | 4 | 5 | 20 | High | Basic WAF rules exist | 2 | 4 | 8 | Medium | In Progress | DevOps | Implement input validation; enable OWASP CRS on WAF | 2025-03-16
R17 | Backup & Recovery | Backups stored in same region as production workloads | 2 | 5 | 10 | Medium | Daily backups to same AZ | 1 | 4 | 4 | Low | Mitigated | IT | Create cross-region backup replication; test DR annually | 2025-03-17
R18 | Privacy / Data Protection | Sensitive data stored without encryption at rest | 4 | 4 | 16 | High | Partial KMS usage | 2 | 3 | 6 | Medium | In Progress | Data Privacy Officer | Migrate to full AES-256 encryption; enforce encryption policy | 2025-03-18
R19 | Vendor Security | Vendor lacks SOC2 Type II report for critical SaaS tool | 3 | 4 | 12 | Medium | Basic contract clauses | 2 | 3 | 6 | Medium | In Progress | GRC Analyst | Require SOC2 attestation; conduct vendor risk assessment | 2025-03-19
R20 | Change Management | Unapproved production changes pushed by engineering | 3 | 4 | 12 | Medium | Manual change log | 2 | 2 | 4 | Low | Mitigated | Engineering Lead | Implement change approval workflow; enforce CI/CD gates | 2025-03-20
R21 | Cloud Infrastructure | Over-provisioned cloud resources increasing cost risk | 1 | 3 | 3 | Low | Basic monitoring dashboards | 1 | 2 | 2 | Low | Accepted | Finance | Implement cost optimization review; rightsizing policy | 2025-03-21
R22 | Physical Security | Server room access logs not reviewed monthly | 2 | 3 | 6 | Medium | Card access enabled | 1 | 2 | 2 | Low | Mitigated | Facilities | Implement monthly access log review SOP | 2025-03-22
R23 | Cybersecurity / Human Risk | Staff unaware of secure document handling procedures | 3 | 2 | 6 | Medium | Basic policy exists | 2 | 1 | 2 | Low | Mitigated | Security Lead | Deploy training; enforce classification scheme | 2025-03-23
R24 | DevOps Security | API keys stored in plaintext in build pipelines | 4 | 4 | 16 | High | Some secrets rotated | 2 | 3 | 6 | Medium | In Progress | DevOps | Move secrets to Vault; enforce short-lived tokens | 2025-03-24
R25 | Third-Party Risk | Critical vendor has no business continuity plan | 3 | 4 | 12 | Medium | Contract clause exists | 2 | 3 | 6 | Medium | In Progress | GRC Analyst | Request BCP docs; integrate vendor into DR testing plan | 2025-03-25
R26 | Application Security | Customer portal vulnerable to brute-force attacks | 3 | 4 | 12 | Medium | Partial rate-limiting | 2 | 2 | 4 | Low | Mitigated | DevOps | Implement MFA; add IP throttling rules | 2025-03-26
R27 | Network Security | Firewall rules overly permissive between internal subnets | 2 | 4 | 8 | Medium | Basic segmentation | 2 | 2 | 4 | Low | Mitigated | Network Engineer | Refine ACLs; implement zero-trust segmentation | 2025-03-27
R28 | Cybersecurity Governance | Policies not reviewed within required annual cycle | 2 | 2 | 4 | Low | Policies exist but outdated | 1 | 1 | 1 | Low | In Progress | CISO | Review and update policies; implement version control | 2025-03-28
R29 | Operational Risk | Single point of failure in customer support escalation path | 2 | 4 | 8 | Medium | Informal SOP | 2 | 3 | 6 | Medium | In Progress | Operations Lead | Implement redundancy; cross-train staff | 2025-03-29
R30 | Cloud Security | Excessive IAM permissions for service roles (overprivileged) | 4 | 3 | 12 | Medium | Limited IAM review | 2 | 2 | 4 | Low | Mitigated | DevOps | Implement least privilege; automate IAM reviews | 2025-03-30

## Dashboard
Risk Register Dashboard
[10 empty] | Total Risks | 5
[10 empty] | High Risks | 5
[10 empty] | Medium Risks | 23
[10 empty] | Low Risks | 2
[10 empty] | Inherent Rating | Count
[10 empty] | High | 5
[10 empty] | Medium | 23 |  |  |  | 1 | 2 | 3 | 4 | 5
[10 empty] | Low | 2 |  |  | 1 | 0 | 0 | 0 | 0 | 0
[14 empty] | 2 | 0 | 1 | 1 | 0 | 0
[14 empty] | 3 | 1 | 1 | 3 | 2 | 0
[10 empty] | Residual Rating | Count |  |  | 4 | 0 | 4 | 8 | 3 | 0
[10 empty] | High Residual Risks | 0 |  |  | 5 | 0 | 4 | 1 | 1 | 0
[10 empty] | Medium Residual Risks | 13
[10 empty] | Low Residual Risks | 17
[10 empty] | Status | Count
[10 empty] | Identified | 0
[10 empty] | Assessed | 0
|  | Likelihood × Impact Heat Map |  |  |  |  | Top Risks | Owner | Score | Mitigation Planned | 0
[7 empty] | SQL injection risk due to unvalidated inputs | DevOps | 20 | In Progress | 14
Likelihood |  | 1 | 2 | 3 | 4 | 5 | Sensitive data stored without encryption at rest | Data Privacy Officer | 16 | Partially Mitigated | 0
| 1 | 0 | 0 | 0 | 0 | 0 | API keys stored in plaintext in build pipelines | DevOps | 16 | Mitigated | 15
| 2 | 0 | 1 | 1 | 0 | 0 | Phishing attack compromises employee account | Security Lead | 16 | Accepted | 1
| 3 | 1 | 1 | 3 | 2 | 0 | Misconfigured S3 bucket exposes customer data | DevOps | 15 | Closed | 0
| 4 | 0 | 4 | 8 | 3 | 0
| 5 | 0 | 4 | 1 | 1 | 0 |  |  |  |  | There are 30 total risks: 5 high, 0 medium, and 2 low. 15 risks are fully mitigated, 14 in progress.
|  |  |  | Impact |  |  | How to Use This Dashboard |  |  | TOTAL RISKS | 30 | TOTAL RISKS 30
[10 empty] | HIGH RISKS | 5 | HIGH RISKS 5
[7 empty] | Instructions Use the slicers on the right to filter risks by date, owner, status, rating, or category All charts and metrics update automatically Do not edit pivot tables or hidden helper cells To add or update risks, use the Risk Register tab only |  |  | MEDIUM RISKS | 23 | MEDIUM RISKS 23
[10 empty] | LOW RISKS | 2 | LOW RISKS 2
[10 empty] | Risk ID | Count of Risk Rating | [8 empty] | Review Date
[10 empty] | R1 | 1 | [8 empty] | 2025
[10 empty] | R10 | 1 | [8 empty] | Qtr1
[10 empty] | R11 | 1 | [8 empty] | Mar
[10 empty] | R12 | 1 | [8 empty] | Grand Total
[10 empty] | R13 | 1
[10 empty] | R14 | 1
[10 empty] | R15 | 1
[10 empty] | R16 | 1
[10 empty] | R17 | 1
[10 empty] | R18 | 1
[10 empty] | R19 | 1
[10 empty] | R2 | 1
[10 empty] | R20 | 1
[10 empty] | R21 | 1
[10 empty] | R22 | 1
[10 empty] | R23 | 1
[10 empty] | R24 | 1
[10 empty] | R25 | 1
[10 empty] | R26 | 1
[10 empty] | R27 | 1
[10 empty] | R28 | 1
[10 empty] | R29 | 1
[10 empty] | R3 | 1
[10 empty] | R30 | 1
[10 empty] | R4 | 1
[10 empty] | R5 | 1
[10 empty] | R6 | 1
[10 empty] | R7 | 1
[10 empty] | R8 | 1
[10 empty] | R9 | 1
[10 empty] | Grand Total | 30
[10 empty] | Risk Rating | Count of Risk ID
[10 empty] | High | 5
[10 empty] | Low | 2
[10 empty] | Medium | 23 | [6 empty] | 30
[10 empty] | Grand Total | 30
[10 empty] | Status | Count of Risk ID
[10 empty] | Accepted | 1
[10 empty] | In Progress | 14
[10 empty] | Mitigated | 15
[10 empty] | Grand Total | 30 | [5 empty] | 30
[10 empty] | Count of Risk ID | Column Labels
[10 empty] | Row Labels | 1 | 2 | 3 | 4 | Grand Total
[10 empty] | 2 |  | 1 | 1 |  | 2
[10 empty] | 3 | 1 | 1 | 3 | 2 | 7
[10 empty] | 4 |  | 4 | 8 | 3 | 15
[10 empty] | 5 |  | 4 | 1 | 1 | 6
[10 empty] | Grand Total | 1 | 10 | 13 | 6 | 30 |  |  | 4
[10 empty] | Residual Rating | Count of Risk ID
[10 empty] | Low | 17
[10 empty] | Medium | 13
[10 empty] | Grand Total | 30 |  |  |  |  | 30
#REF!
TOTAL RISKS 30
HIGH RISKS 5
MEDIUM RISKS 23
LOW RISKS 2
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
SUMMARY
There are 30 total risks: 5 high, 0 medium, and 2 low. 15 risks are fully mitigated, 14 in progress.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
SholaHassan